## Sheet1
Story ID | Priority | Story Title | As a.. | I want to.. | so that.. | Acceptance Criteria | Notes | Story Points | Complexity
1 | M | Register Membership | Non-Member | Register as a member | I can become a registered member of the community | Account creation confirmation email is sent to the member |  | 1 | 1
2 | M | Create Events | Committee Member | Create an event | Members register their attendence and donate | Event information is displayed to all committee members in event list |  | 2 | 2
3 | S | Alter Event Information | Committee Member | The ability to alter event information | Members are notified of event updates | Involved committee members recieve a notification that an event detail has changed |  | 4 | 4
4 | S | Cancel Events | Committee Member | Cancel an event | Members are notified and can not join them | Event information is no longer displayed to committee members |  | 4 | 4
5 | S | Notify Events | Committee Member | Notify all members when a new event is planned | Members will be updated of any planned events | A notification is sent to members when an event is being planned |  | 8 | 6
6 | M | Set Event Cost | Committee Member | Set the estimated cost for events | Donations/ sponsorship can be called | Cost details changed in event details listing |  | 1 | 1
7 | S | Call For Donations | Committee Member | The ability to call for donations | Members can start donating to the event | A notification is sent to donors/sponsors asking for donation |  | 8 | 6
8 | M | Event Cost Shortfall | Committee Member | Track event cost shortfall | I can check the difference of the initial estimated cost versus the final cost | Running total of cost shortfall is displayed in event details |  | 8 | 6
9 | M | Event Donation Tracking | Committee Member | View the amount donated to an event | I can track how much donation has been contributed to an event | Running total of money donated to an event in event deatils |  | 8 | 8
10 | C | Events Fee Deadline | Committee Member | Choose cut-off date for receiving money | I can collect events fee | Cut-off date is displayed in the event details |  | 2 | 2
11 | C | Recruit Volunteers | Committee Member | Ask members to volunteer in events | The events will be much easier to handle | Volunteering notification is sent to members |  | 8 | 6
12 | S | Total Donation Tracking | Committee Member | Check the member's donation to an event | I can see who donates generously | Donation information by donor is displayed to committee members in event details |  | 8 | 6
13 | M | Create Special Events | Committee Member | Create a special event | Honour donors who has donated more than $3000 | When donations are called for, donors who have donated over $3000 do not recive a notification |  | 2 | 2
14 | C | Honour Donors Notification | Committee Member | Be notified when a member has donated more than $3000 | I can create special events to honour donors | When a member has donated a total of $3000, a notification is sent to committee members |  | 4 | 4
15 | C | Share Events | Committee Member | Share the events on facebook | It is easier for members who are using facebook | A Facebook post for an event is made | Unsure if implementable | 16 | 12
16 | M | View Events | Member | View any available events | I can join if interested | Upcoming event informaiton is displayed to members | Unsure if filter is implementable | 8 | 6
17 | C | Receive Event Notification | Member | Receive notification regarding any events | I can get any events updates | Notification is given when significant event detials change | Unsure if FB notification is implementable | 16 | 12
18 | M | Register Attendance | Member | Be able to register my own and my family’s attendance | The committee members will know who would attend the event | A notification of event registration. Event shows in calendar of upcoming events being attended |  | 8 | 6
19 | C | Withdraw Attendance | Member | Be able to remove my own and my family’s attendance | The committee members will know who would attend the event | A notification of confirmation of withdrawl. Event no longer shows in calendar of upcoming events being attended |  | 8 | 8
20 | M | Check Event Fee | Member 18+, no donation | Know the amount I need to pay for each event | I can pay accordingly | Estimated event fee is displayed in the event detials |  | 4 | 4
21 | M | Check Special Event Fee | Member 18+, donate < $500 per event | Know how much I need to pay for any special events | I can pay accordingly | Estimated event fee is displayed in the event detials |  | 4 | 4
22 | M | Register Volunteering | Member | Be able to register as a volunteer in an event | I can volunteer in the events | A notification of cofirmation with details of volunteering duties is sent to member |  | 4 | 4
23 | C | Withdraw Volunteering | Member | Be able to remove my volunteering in an event | I can decline volunteering in the events | A notification of cofirmation of withdrawl is sent to member |  | 4 | 4
24 | C | Select Volunteering Task | Member | Be able to chose the volunteering task I want | I can volunteer in the areas I am familiar with | A notification of cofirmation with details of volunteering duties is sent to member |  | 8 | 6
25 | C | Deselect Volunteering Task | Member | Be able to remove the volunteering task | I can choose other areas I am familiar with or not volunteer | A notification of cofirmation of withdrawl is sent to member |  | 4 | 4
26 | M | View Attending Events | Member | View the events I am attending | It reminds me which events I would need to go | Events registered for are displayed in calendar of upcoming events being attended |  | 8 | 6
27 | M | View Volunteering Events | Member | View the events I am volunteering | It reminds me which events I would need to volunteer | Events I am volunteering in are marked in calendar of upcoming events being attended |  | 8 | 6
28 | C | View Volunteering Task | Member | View the available task for volunteer in an event | I can check which task I can volunteer in | Details of volunteering duties are displayed when I view event information |  | 2 | 2
29 | M | View Event Donations | Member | Know how much donation have been allocated to each event | I can determine if the events needs donation or not | The donation cost is displayed in the event information |  | 8 | 6
30 | M | Set Donations Amount | Member | Be able to choose how much I donate | I can donate the amount I want to give | Donation amount is updated on the event details |  | 2 | 1
31 | S | View Donations Log | Member | Be able to track how much I donate to each event | It can become my donation guide | Transactions made to the organisation show in transaction history |  | 4 | 4
32 | C | View Donations Details | Member | Know what the money I donate contributes to | I can donate to the right deed | Cost of elements of events are displayed when requested |  | 16 | 12
33 | C | History Log | Member | View my attended, volunteered, donated events | I can see my activeness in the community | Event attendance, registration and details are displayed in history log |  | 8 | 8
34 | C | Edit Profile | Member | Edit my information | I can update my new information | New personal information is displayed in my details |  | 4 | 4
35 | M | Log In | Anyone ex Non-member | Log in the website when I start using the website | Information are secured | The landing page is displayed |  | 2 | 2
36 | M | Log Out | Anyone ex Non-member | Log out the website when I finish using the website | Information are secured | The login page is displayed when trying to access any page on the website |  | 2 | 2
37 | S | View Attendee List in event | Anyone ex Non-member | View the attendee list of the event | I know who will know who would attend the event | Attendee list and total attendance is displayed in the event details |  | 2 | 2
38 | S | View Volunteer List in event | Anyone ex Non-member | View the volunteer list of the event | I know who will know who would volunteer in the event | Volunteer roles and volunteering people is displayed in the event details |  | 2 | 2
39 | C | Donor Donation tracking | Donor (Non-member) | View a history of my donations to events | I can track how much I contribute to an event | Donations are displayed in donation history |  | 8 | 4
40 | M | Host website on a domain | Anyone | Be able to access the website via the internet | I can view it anywhere | Website loads without errors |  | 2 | 2
| Total | [6 empty] | 229 | 190